Master Project Plan

Cyber Competition Training Curriculum Development for Cyber Games

Project Lead: Vinay Kagitha  |  Mentor: Dr. John Goulden
Department: Computer Science  |  Target Duration: 6 Months
Progress Meeting: Every Tuesday

# 1. Project Overview

This project will design, develop, test, and document a cybersecurity training curriculum that prepares students for individual and team-based cyber competitions, including the National Cyber League (NCL) and National Centers of Academic Excellence (NCAE) Cyber Games.

The curriculum will begin with foundational knowledge and progress toward realistic competition scenarios. Instructional content will be organized around common cybersecurity knowledge domains shared across multiple competition formats.

# 2. Project Goals

Develop a reusable instructional repository.

Create complete workshop materials and hands-on lab exercises.

Develop instructor guides, student guides, and presentation slides.

Create and document virtual lab environments.

Develop practice competition exercises and readiness materials.

Create a complete 14-week workshop schedule.

Validate the curriculum and prepare it for adoption.

# 3. Success Criteria

All 12 instructional modules are completed.

Every module includes slides, labs, instructor notes, and student guides.

At least one hands-on assessment is created for each module.

A complete 14-week workshop schedule is developed.

A mock NCL-style competition is created.

A mock NCAE Cyber Games scenario is developed.

All lab environments are tested and documented.

# 4. Module Structure

| Module | Title | Primary Topics |
| --- | --- | --- |
| 1 | Foundations | Linux, Windows, networking fundamentals, virtualization, Git/documentation |
| 2 | Defensive Operations | Windows/Linux hardening, firewall configuration, user management, secure services, patch management, logging, SIEM, incident response, backup |
| 3 | Networking | Packet analysis, Wireshark, TCPDump, network mapping, IDS/IPS, Snort, Suricata |
| 4 | Digital Forensics | Event logs, memory analysis, registry, browser artifacts, Volatility, Autopsy |
| 5 | Cryptography | Classical ciphers, AES, RSA, hashing, JWT, Base64 |
| 6 | Password Security | Hashcat, John the Ripper, password policies, MFA |
| 7 | Web Security | SQL injection, XSS, CSRF, Burp Suite, OWASP Top 10 |
| 8 | Reverse Engineering | Assembly, Ghidra, GDB, static analysis, dynamic analysis |
| 9 | Enumeration & Exploitation | Nmap, SMB, LDAP, CVEs, privilege escalation, Metasploit |
| 10 | OSINT | Google Dorking, WHOIS, DNS, GitHub reconnaissance, Shodan, Maltego |
| 11 | Capture the Flag Skills | Methodology, writeups, CyberChef, Pwntools, automation |
| 12 | Competition Readiness | Team roles, communication, documentation, stress management, scoreboard strategy |

# 5. Standard Deliverables for Each Module

Learning objectives and prerequisites.

Presentation slides.

Instructor guide / lesson plan.

Student guide / workbook content.

Hands-on lab exercise(s).

At least one hands-on assessment or challenge.

Quiz / assessment questions where appropriate.

Solutions, instructor notes, or validation guidance.

Required tools, software, VM/environment requirements.

Lab testing and documentation.

# 6. Six-Month Master Timeline

| Month | Focus | Objectives | Key Deliverables |
| --- | --- | --- | --- |
| Month 1 | Planning and Foundation | Finalize curriculum framework; build GitHub repository; configure lab environment; create templates; develop Module 1. | Project repository; Module 1 complete; development standards; VM baseline. |
| Month 2 | Core Infrastructure | Develop Modules 2, 3, and 4. | Blue Team labs; networking labs; forensics labs. |
| Month 3 | Offensive Security Content | Develop Modules 5, 6, and 7. | Cryptography labs; password labs; web security labs. |
| Month 4 | Advanced Technical Topics | Develop Modules 8, 9, and 10. | Reverse engineering labs; enumeration labs; OSINT labs. |
| Month 5 | Competition Development | Develop Modules 11 and 12; create mock competitions, scoring system, and team exercises. | Complete competition package. |
| Month 6 | Validation and Deployment | Pilot the curriculum or review the plan with the team; refine materials; prepare for adoption next semester. | Pilot workshop implementation plan; student/faculty feedback forms and summary; revised instructional materials; instructor handbook; final curriculum repository. |

# 7. 26-Week Working Roadmap

| Week | Focus | Primary Work | Expected Output |
| --- | --- | --- | --- |
| 1 | Project setup | Confirm scope, requirements, success criteria, and working standards. | Project structure and task tracker |
| 2 | Curriculum architecture | Define common module template and repository structure. | Templates + repository structure |
| 3 | Lab foundation | Establish VM baseline and lab documentation standards. | Baseline environment |
| 4 | Module 1 development | Complete Foundations content, slides, guides, labs, and assessment. | Module 1 draft/complete |
| 5 | Module 1 validation | Test labs and revise Module 1. | Validated Module 1 |
| 6 | Module 2 | Develop Defensive Operations materials and labs. | Module 2 draft |
| 7 | Module 3 | Develop Networking materials and labs. | Module 3 draft |
| 8 | Module 4 | Develop Digital Forensics materials and labs. | Module 4 draft |
| 9 | Core module testing | Test Modules 2–4 and document issues. | Validated Modules 2–4 |
| 10 | Module 5 | Develop Cryptography materials and challenges. | Module 5 draft |
| 11 | Module 6 | Develop Password Security materials and lab. | Module 6 draft |
| 12 | Module 7 | Develop Web Security materials and lab. | Module 7 draft |
| 13 | Offensive module testing | Test Modules 5–7 and revise. | Validated Modules 5–7 |
| 14 | Module 8 | Develop Reverse Engineering materials and exercises. | Module 8 draft |
| 15 | Module 9 | Develop Enumeration & Exploitation materials and exercises. | Module 9 draft |
| 16 | Module 10 | Develop OSINT materials and scavenger hunt. | Module 10 draft |
| 17 | Advanced module testing | Test Modules 8–10 and revise. | Validated Modules 8–10 |
| 18 | Module 11 | Develop CTF methodology, writeups, CyberChef, Pwntools, automation. | Module 11 draft |
| 19 | Module 12 | Develop Competition Readiness materials and rubric. | Module 12 draft |
| 20 | Competition design | Develop mock NCL-style and NCAE-style competition concepts. | Competition framework |
| 21 | Competition implementation | Build challenges, scoring, team exercises, and documentation. | Complete competition package |
| 22 | 14-week workshop | Finalize workshop sequence and map modules to sessions. | 14-week workshop schedule |
| 23 | Pilot preparation | Prepare pilot materials, feedback forms, instructor handbook draft. | Pilot package |
| 24 | Pilot / internal review | Conduct pilot or structured team review and collect feedback. | Feedback + issue log |
| 25 | Revision & final validation | Revise materials and retest critical labs. | Revised curriculum |
| 26 | Deployment | Finalize repository, documentation, instructor handbook, and adoption package. | Final curriculum repository |

# 8. Tuesday Progress Meeting System

Every Tuesday will serve as the project's formal progress checkpoint. The goal is to maintain continuous visibility, obtain feedback early, and prevent major problems from accumulating.

Completed since the previous meeting.

Current work in progress.

Planned work before the next Tuesday.

Problems, blockers, or technical issues.

Feedback or decisions needed from the mentor/Chair.

Changes to scope, timeline, or priorities.

Updated evidence: repository commits, completed materials, tested labs, drafts, or feedback.

# 9. Weekly Tuesday Meeting Record Template

Date:

Week:

Completed:

In Progress:

Next Week:

Blockers/Risks:

Questions/Decisions Needed:

Feedback Received:

Action Items:

# 10. Project Tracking Principles

Plan for completion within six months while retaining the option to request additional time if necessary.

Do not consider a module finished until its required instructional and technical components are created and tested.

Use a consistent structure across all modules to make the repository reusable.

Test labs before pilot delivery and document setup, expected results, and known issues.

Capture mentor/Chair feedback and incorporate revisions into the project record.

Maintain version-controlled project materials so progress and revisions are traceable.

Keep a small amount of schedule flexibility for technical issues, feedback, and pilot revisions.

# 11. Key Risks to Monitor

| Risk | Potential Impact | Mitigation |
| --- | --- | --- |
| Lab environment complexity | Labs may take longer than expected to build or troubleshoot. | Build and test environments early; maintain a VM baseline. |
| Content scope expansion | Additional topics can expand the project beyond six months. | Keep the approved 12-module scope as the baseline. |
| Testing delays | Untested labs can create downstream problems. | Test incrementally instead of waiting until Month 6. |
| Feedback/revision cycles | Mentor or Chair feedback may require substantial revisions. | Use Tuesday meetings as recurring review checkpoints. |
| Competition development workload | Mock competitions can become a separate large project. | Reuse module challenges and common infrastructure where appropriate. |

# 12. Final Project Package

12 completed instructional modules.

Slides for all modules.

Instructor guides / lesson plans.

Student guides / workbooks.

Hands-on labs and assessments.

Virtual lab environments and documentation.

14-week workshop schedule.

Mock NCL-style competition.

Mock NCAE Cyber Games scenario.

Blue Team exercises and CTF challenges.

Scoring rubrics and team readiness materials.

Instructor handbook.

Pilot implementation plan and feedback materials.

Final reusable curriculum repository.

# 13. Source Basis

This master plan is based on the Faculty Project Guide provided for the project. The guide identifies the six-month sequence, 12 recommended modules, expected deliverables, competition resources, and project success metrics. The 26-week breakdown and Tuesday meeting workflow above are project-management organization added to operationalize those requirements.